## Slide 1: Tableau UAT Project Updates
06th December 2024

## Slide 2: Tableau UAT Project Milestones Status – 05th December 2024
Planned Milestones | Owner | Completion/Target Date | Current Status | Challenges/Dependencies
Dashboard Validation & UAT Status |  |  |  | 
Data source creation using SQL in DEV environment 40 | BI – Harshala | 9th Nov 2024 | Metrics validated/feedbacks worked | Access to Tableau desktop
Creation of extracts for all the 22 Data sources | BI – Harshala | 16th Nov 2024 | Completed | Alteryx to AWS/Athena Infra challenges
Validation of 320+ calculated fields with Athena mapping | BI – Harshala | 18th Nov 2024 | Completed | Data source format discrepancies.
Switch tableau dashboard to updated AWS data sources | BI – Harshala | 20th Nov 2024 | Completed | Volumes of data and processing times
Creating Schedules for extracts on dev server | BI – Harshala | 3rd Dec 2024 | Completed | Ingestion of data into the tables
Testing and Validating Views in dashboards | BI – Harshala | 5th Dec 2024 | In Progress | Anoop to confirm source data
User acceptance testing (UAT) | BI – Harshala | 6th Dec 2024 | In Progress | Go Ahead Approval from Zach
Performance testing (speed, data load). | BI – Harshala | TBD | Yet to start | Performance issues with new data loads.
Look And feel Changes as will be agreed on Dashboards |  | TBD |  | Features Compatibility of existing dashboard
Migration To prod | BI-Harshala | TBD |  | Alignment with the Cox Team (Zach)
CB Digital Pulse | BI-Harshala | TBD | Yet To start | Anoop / Suresh to generate data in AWS
Validate identified Data sources linked with the dashboards
Updating & validating queries, Creation Of extracts
Publish dashboard to Dev Environment
Testing & validation of Tableau dashboard views
Creating and Mapping of Calculated fields
Migration to Production Environment
NOV 09TH
NOV 16TH
Nov 20TH
Dec 2ND
TBD
Dec 6TH
Medium Risk
Meets the Plan

## Slide 3: Data Dependencies and Identified Issues Status – 05th December 2024
Data Sources Issues Identified Status |  |  |  |  | 
Work flow creation in Alteryx = 56 | Data – Anoop/Suresh | 9th Nov 2024 | Completed |  | To be confirmed by Anoop/Suresh
Update data tables in Athena | Data – Anoop/Suresh | 27th Nov 2024 | Completed |  | Volumes of data and processing times
DS issue with DS order funnel DS fore cast, DS Alerts,) , | Data – Anoop/Suresh | 3rd DEC 2024 | In process |  | To be confirmed by Anoop/Suresh
CB Chat Sessions (Marketing, DS CB Mktg Channel | Data – Anoop/Suresh | 14th Nov 2024 | Yet to Start |  | To be confirmed by Anoop/Suresh
CB Marketing Source - call metr, DS CB Campaigns, SFO - Sales Order Details | Data – Anoop/Suresh | 13th Nov 2024 | Yet to Start |  | To be confirmed by Anoop/Suresh
CBForce Leads, DS CB Buyflow, DS CB Page Type ¦ Project : Coll | Data – Anoop/Suresh | 14th Nov 2024 | Yet to Start |  | To be confirmed by Anoop/Suresh

## Slide 4: UAT 12 Dashboard Status December 5, 2024
Upcoming Tasks
Digital Daily Digest Dashboard Views:
Upcoming week Dashboard View Testing
 | Data sources on Deve server |  | Updated Calculated fields |  | Validation | 
1. DS Affordability Leads |  |  | 21 |  |  | 
2. DS Affordability Offer Device Type |  |  | 16 |  |  | 
3. DS Affordability Orders Leads |  |  | 34 |  |  | 
4. DS Affordability Page Driver |  |  | 14 |  |  | 
5. DS Buying Cycle |  |  | 26 |  |  | 
6. DS Connects |  |  | 62 |  |  | 
7. DS Forecast |  |  | 24 |  |  | 
8. DS Targets |  |  | 31 |  |  | 
9. DS Revenue Daily |  |  | 91 |  |  | 
10. DS Mktg Channels |  |  |  |  |  | 
11. DS All Buying Cycles |  |  | 26 |  |  | 
12. DS Offer by Quality Type |  |  | 21 |  |  | 
13. DS Page Type by Quality Type |  |  | 9 |  |  | 
14 DS Revenue Details |  |  | 44 |  |  | 
15 DS Non Customer Cycles |  |  |  |  |  | 
16 DS Flow by Quality Type |  |  | 15 |  |  | 
17 DS DMAS Scorecard |  |  |  |  |  | 
18 DS Revenue |  |  | 44 |  |  | 
19 DS Sellin |  |  |  |  |  | 
20 DS Order Funnel Daily |  |  | 21 |  |  | 
21 DS Order Funnel |  |  | 81 |  |  | 
22 Goals (2023 MDU Scorecard Metrics) |  |  |  |  |  | 
23 |  | DS Alerts | 34 |  |  | 
Dashboards
https://bi-viz.corp.cox.com/#/views/ConnectsDashboard/ChannelShare
https://bi-viz.corp.cox.com/#/views/Affordability/TECodeAudience
https://bi-viz.corp.cox.com/#/views/DigitalDailyDigest/DailyDigest
https://bi-viz.corp.cox.com/#/views/DigitalPulse2_0/Summary
https://bi-viz.corp.cox.com/#/views/HistoricalKPIs/Revenue
https://bi-viz.corp.cox.com/#/views/NCRs/OnlineNCRs
https://bi-viz.corp.cox.com/#/views/OrderFunnelDashboard/OrderFunnelTrends
https://bi-viz.corp.cox.com/#/views/Revenue/OnlineRevenue
https://bi-viz.corp.cox.com/#/views/SalesProjections/Summary
https://bi-viz.corp.cox.com/#/views/MDUQuickConnectDashboard/NCR?:iid=5
https://bi-viz.corp.cox.com/#/views/NCRevenueDocument-Tables/NCRevenueTables
https://bi-viz.corp.cox.com/#/site/CSBI/workbooks/19041/views

## Slide 5: Tableau UAT Project Status
Weekly Key Headlines
Risks & Issues
Testing Checklist
Data Accuracy: Ensure data from the new source is accurate and consistent.
Performance: Test dashboard load times with the new data.
Error Handling: Check for error messages, broken links, or missed data points.
Functionality: Ensure that all dashboard features are working as expected.
Program Objective
The primary objective is to integrate a new data source into the existing ecosystem of 12 dashboards, ensuring seamless data flow and functionality across all dashboards. This process includes: Testing: Thoroughly testing the dashboards to validate data accuracy, performance, and overall system integration with the new data source. Dev Environment Integration: Switching all relevant dashboards to the development environment to ensure that the new data source integrates properly, without affecting the current system or performance. Data Consistency: Ensuring that the new data source aligns with the current data models and dashboard requirements for all 12 dashboards, with a focus on maintaining data consistency and integrity. Performance Optimization: Conducting performance testing to assess the load times and responsiveness of the dashboards with the new data source in place. Validation & Sign-Off: Ensuring stakeholder approval by reviewing results and confirming that the dashboards perform as expected with the new data source. Deployment: Finalizing the switch to production once the development environment testing phase is completed successfully. By achieving this objective, the team aims to enhance the accuracy, reliability, and efficiency of the 12 dashboards, ensuring that they are ready for use in a live environment with optimal performance.
Integrating New Data Source into Dev Environment
1: Data mapping and extraction from the new data source.
2: Update dashboard queries and data models.
3: Test data population and integration into dashboard.
4: Validate data accuracy with sample test cases.
Key Considerations for Switching Dashboards to Dev Environment
Data Validation: Ensure the new data source matches expected formats and values.
Performance Testing: Check for speed and responsiveness with the new data source.
System Checks: Verify that the new data source does not interfere with existing data flows or system operations.
Objective
Issues With Data Source | Description |  |  |  | 
DS issue with DS order funnel | Data sorce data need to be present in athena |  |  |  | 
DS fore cast, | Accuracy of data is needed |  |  |  | 
DS Alerts,) , | Recent data Need to be present. |  |  |  | 
CB Chat Sessions (Marketing, DS CB Mktg Channel |  |  |  |  | 
CB Marketing Source - call metr, DS CB Campaigns, SFO - Sales Order Details |  |  |  |  | 
CBForce Leads, DS CB Buyflow, DS CB Page Type ¦ Project : Coll |  |  |  |  | 

## Slide 6: Thank You