## Project Plan
Activities |  | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04
Data Engg | Individual Accesses & Azure AVD set up
Discovery & Requirement Gathering
Accesses and Enviroment Setup (AWS)
Data Ingestion (S3)
Creating Pipeline & Orchestration
Data Transformation (Sage maker/ ETL)
Query (Athena)
Monitoring & Automation
Testing & Validation
BI Development | Sample data procurement & understanding
Visualization Design
Development
Connections with Athena/AWS
Testing & Validation
Deployment & Support

## Data Architecture
Implementation Roadmap for AWS
Data Sources | Data Classification
Oracle DB (Table-Schema) | Structured
Glu/ Sage maker/ PySpark/ EMR
Splunk (Log files) | Unstructured |  | AWS DMS, Custom Scripts, Lambda function,Direct Upload
|  |  |  | AWS S3 (Landing Stage) | Sage Maker (ETL) - Staging Stage |  | S3 Processed Data Bucket | Athena
S3 (File) | Semi Structured
CRM Application (DB) | Structured
|  |  |  | S3 as Primary data lake to store raw data | Data Cleansing, Filter, Transformation |  |  | Athena to run SQL queries on the data stored in S3 processed bucket
[6 empty] | Tableau |  | Athena External Table

## Data Model 1-customer data (hidden)
|  | remove | remove | [7 empty] | Remove | Remove
Column Name | GUID | user_id | Registration_Type | Registation_Time | Verified Contact | Verified_type | Email Verified | Phone Verified | Market(US cities) | Business_Type | Email_Info | Contact_details | Recovery type | TSV registered | TSV Adoption type | Feature | Engagement Channel | Login_timestamp | Service/Product_subscription | Address | Registration_type | Customer_status | Customer vistied to site
Data Type | UNIQUEIDENTIFIER | VarChar(50) | String | Timestamp | string(5 char) | VarChar(50) |  |  | string (50 char) | string (50 char) | VarChar(50) | Int(10) | varchar(50) | string | string | string | string
Attributes | Primary Key(Alphanumeric) |  | Auto-Registration | user when register first time | Yes/No | Email/Phone |  |  | 29 cities we need to consider | Commercial/Residential |  |  | Phone/SMS/email | Yes/No | Email/call/SMS/Okta | Authentication/Password Reset/User ID Recovery | Digital, Call Center, Retail
Sample Data | 001 6311 064810301 | praveenp | web/App | 2024-08-12T13:58:18+00:00 | Yes/No | Email |  |  |  | Residential | Praveen.Prabhakaran@cox.com | XXXX | Email | Yes/No | Okta | Password Reset | Digital
Source | Customer GUID Detail |  |  | Customer GUID Detail
Flags
[5 empty] | Email | Incpetion date
[5 empty] | Phone | Registration date
[5 empty] | Email Verified | Acquisition Channel
[5 empty] | Phone Verified | User Permissions [Basic/ Advance]
[5 empty] | Primary | TSV Status
[5 empty] | TSV Email | Preferences [ 3 columns]
TSV Phone
TSV SMS

## Data Models
Customer Profile
Column Name | GUID | Inception Date | Registation_Time | Email | Phone | Verified Contact | Verified_type | Email Verified | Phone Verified | Market(US cities) | Business_Type | Is_Primary | Recovery type | TSV Status | TSV EMAIL | TSV Phone | TSV SMS | Acquistion Channel | User Permission | Preference 1 | Preference 2 | Preference 3 | Digital | Visits | Sessions
Data Type | UNIQUEIDENTIFIER | Timestamp | Timestamp | string | string | string(5 char) | VarChar(50) |  |  | string (50 char) | string (50 char) | boolean | varchar(50) | string | string |  |  | string
Attributes | Primary Key(Alphanumeric) | Customer inception time | user when register first time | Has a email [1/0] | Has a Phone[1/0] | [1/ 0] | Email/Phone |  |  | 29 cities we need to consider | Commercial/Residential | [1/0] | Phone/SMS/email | [1 /0 ] | Email/call/SMS/Okta |  |  | Digital, Call Center, Retail | Basic/ Advance |  |  |  | [App / Web]
Sample Data | 001 6311 064810301 | 2024-08-12T13:58:18+00:00 | 2024-08-12T13:58:18+00:00 |  |  | 1 | Email |  |  |  | Residential |  | Email | [ 1 ] | Okta |  |  | Digital
Source | Customer GUID Detail |  | Customer GUID Detail
Customer Activity
Column Name | Authentication ID | Customer ID / GUID | Auth Method | Editable User Id | OTP Token | OTP Sent Date | OTP verification Status | PasswordHash | PasswordLast Updated | LastSuccessfulLoginDate | AuthAttemptDate | Channel Type | AuthStatus | Channel Type | AuthMethod | AgentID | Retail Location | Recovery ID | Recovery Method | Recovery Status | RecoveryRequestDate | RecoveryCompletionDate | Recovery Failure Reason | Method | Verification Status | Email Verified | Phone Verified | Account Verified | Is_ Security Questions | Answer Success | AuthSuccessID | Channel Type | Auth Method | Auth Status | AuthenticationTimeLimit
Data Type | Varchar | UNIQUEIDENTIFIER | String | Boolean | String / Integer | DateTime | String | Varchar | DateTime | DateTime | DateTime | String | String | String | String / Integer | Varchar | String | Varchar | String | String | DateTime | DateTime | String |  | String | String | String | String | String | String | Varchar | String | String | String | DateTime
Attributes |  | Primary Key(Alphanumeric) | Passwords, OTP | 1, 0 | 1,0 |  | Verified, NotVerified, Expired |  |  |  |  | Web, App | Successful, Failed, Pending | IVR, Retail [Offline] | OTP |  |  |  | Phone, Email, Account Details | Requested, InProgress, Completed , Failed |  |  |  |  | Verified, Not Verified | 1 , 0 | 1, 0 | 1, 0 |  | 1, 0 |  | Email, Call, SMS | OTP, Password | Successful, Failed
Sample Data
Source

## Customer _Profile_Metric
Customer Enabled Information |  |  |  |  | Filters/ Slicers
Metric | Calculation | Columns | Source Table |  | Market
Total Customers | Count of GUID's (Account) | GUID (Account) | Customer_dim |  | Business Type = Residential
Total Registered Customers | Total GUID (User) | GUID's User | Customer_dim |  | User type
Total GUID's | User/Profile | GUID (User, Account) | Customer_dim |  | Inception date
Registration |  |  |  |  | Registration Type
Auto-Registration | Count of auto register = 1 | Auto Registered (1, 0) | Customer GUID detail level |  | Registration Date
% of Customers Registered | (Total (User GUID)/ Total(Account GUID))*100 | GUID (Account, User)
Registered_7days/30_Days_90_days | Date Diff between Inception and Registration date, based on 7 days filter | Registration Date
Inception Date
Acquisition Channel |  |  |  | Throgh Social Media, Adv,Newspaper
Success in Registration | count(Regisered_user) where registered_user='1' | Registered User
Email Success | (count(email_verified) where email_verified='1')/total registered user | email_verified
total registered user
Phone Success | (count(phone_verified) where phone_verified='1')/total registered user | phone_verified
total registered user
Account Success | Count of registered user | Account ID
Registered User
Verified Contact Data
0tification Preference | Distinct count of Preference Type | Preference Type(sms,email)
Atleast 1 method Verified | Count(Regisered_user) where verified_user='1' | Verified_User
Resgistered_user
More than 1 method verified | 1 - Atleast 1 method Verified | Phone Verified
Email Verified
Email Verified | (count(email_verified) where email_verified='1') | Email_verified
Total registered user
Phone Verified | (count(phone_verified) where phone_verified='1') | Phone_verified
Total registered user
Both Verified (Email, Phone) | (count(phone_verified) & ( email_verified) where phone_verified & email_verfied ='1') | Phone verified
total registered user
email_verified
TSV Adoption | sum(TSV Registered) whereTSV Registered='1' | TSV registered
TSV Email verified | count of tsv registered where tsv type='email' | Email Verified
TSV Type
TSV phone verified | count of tsv registered where tsv type='call' | Phone Verified
TSV Type
TSV SMS verified | count of tsv registered where tsv type='sms' | TSV Type
Sms Verified
Age of Contact

## Customer_Activity_Metrics
Customer Authentication Information
Metrics | Calculation | Columns | Source table | Filters/Slicers
Total Customers | Count of Account GUID | Account GUID |  | Market
Authentication |  |  |  | Business Type = Residential
Editable user ID |  |  |  | User type
OTP as |  |  |  | Inception date
Authentication Success % | Count of auth ID / Total cust * 100 | Auth ID |  | Registration Type
User Type | Count of Primary / Total cust * 100 and Secondary users/ Total cust * 100 | Count of Account GUID |  | Registration Date
|  | User Type |  | Channel Type
Channel Type | Filter/ Slicer | Channel type |  | TSV Type
Digital % | Count of Digital / Total Channel type * 100 | Channel type
Channel type
Web % | Count of Web auth user/ Total Digital user * 100 | Digital User
Digital Auth Type
App % | Count of app auth user / Total Digital user * 100 | Digital User
Digital Auth Type
Offline % | Count of Offline / Total channel type * 100 | Channel type
IVR % | Count of IVR / Total offline Auth user * 100 | offline Auth Type
Retails % | Count of Retail / Total offline auth user * 100 | offline Auth Type
Credentials
Recovery Success % | (Count of Recovery ID where Recovery_Status as 'success'/ count of Recovery ID) *100 | Recovery ID
Recovery status
Phone % | (Count of Recovery ID where Recovery_method as 'Phone' and Recovery status as success / count of Recovery ID) *100 | Recovery ID
Recovery Status
Recovery method
Email % | (Count of Recovery ID where Recovery_method as 'Email' and Recovery status as success / count of Recovery ID) *100 | Recovery ID
Recovery Status
Recovery method
Account % | (Count of Recovery ID where Recovery_method as 'Account' and Recovery status as success / count of Recovery ID) *100 | Recovery ID
Recovery Status
Recovery method
TSV Enrollment
TSV Auth Success % | count of TSV Registered='Yes' / Total TSV Registered)*100 | TSV register
Email % | (Count of TSV Registered= 'Yes' and TSV Type ='email' /Total TSV Registered)*100 | TSV register
TSV Type
Call % | (Count of TSV Registered= 'Yes' and TSV Type ='call' /Total TSV Registered)*100 | TSV register
TSV Type
Sms % | (Count of TSV Registered= 'Yes' and TSV Type ='sms' /Total TSV Registered)*100 | TSV register
TSV Type
Metric from dashboard sheet
Users with Secondary Permission | count of user type="secondary" | user type
Users with Authorized Permission | count of user permission='authorized' | user_permission
Authentication by Channel by method | Count of User GUID group by 'channel' and 'Auth method' | Auth Method
User GUID, Channel
Users with defined prefrence |  | User preference
users with TSV Enabled | count of TSV enabled='Yes' | TSV enabled
TSV Factor | count of TSV type='sms' and 'email' | TSV Type
Engagement
Average Time from Order to Install | AVG(DATEDIFF 'day', [order date], [Install date]) | Order date
Install date (installation completion date)
Order date
Average Time from order to register | AVG(DATEDIFF 'day', [order date], [Registration date]) | registration date
Average Time from order to First Digital Contact | AVG(DATEDIFF 'day', [order date], [Inceptiondate]) | Inception date
Order date
% of customers seeing an onboarding email | Count of User GUID where Onboarding email seen = True) / Count of user GUID)*100 | User GUID
Onboarding email seen
% of customer logging in last 3 months | (count of User GUID where LastLoginDate in past 3 months /total User GUID))*100 | User GUID
Last Login Date
% of customers downloading the app | Count of User GUID where App Downloaded = True / Count of USer GUID *100 | GUID
App downloaded
TSV Reset Volume and Success Rate
% of Customers registering on F1
TSV Authentication Volume and Success Rate
Total Contact by channel by Sales/Serve
User logged in past 12 months | Count of User GUID where LastLoginDate is within past 12 months | User GUID
Last Login Date

## Data Model 1 customer Profile (hidden)
Metric | Calculation | Columns Required to calculate metric | Column | Data Type | Attribute | Description | Column Source
Total Customers | Count of GUID | GUID (Account) | GUID (Account) | Varchar | Primary Key(Alphanumeric) | Identifier linking to customer | Customer_dim
Success Registered Customers % | Reg_customers/ count(total_customers) |  | GUID (Account) |  | Primary Key(Alphanumeric) | For login & password | Customer_dim
|  |  | GUID 2 (User) | Varchar | User level (Foreign Key) | User level ID associated with primary account
Total GUIDS (User/Profiles) | Total no of Account GUID | Total GUID (user)/total GUID(Account) | Customer Key | Int | Primary Key | Internal Key (6 - 8 digit)
Registered within 7 days | DateDiff('days', Registration date,7) | Registration Date | User Permission |  | Primary User ,Secondary User
Success in Registring | count(Regisered_user) where registered_user='YES' | Registered_user | User Authentication |  | Authorized/Unauth
Email Registration | (count(email_verified) where email_verified='Yes')/total registered user | email_verified,total registered user | Notification preferences | String | Email/ Phone (Call/SMS)
Phone Registration | (count(phone_verified) where phone_verified='Yes')/total registered user | phone_verified,total registered user | Market | String | 29 cities we need to consider | 26 Cities (Need to check)
Both Registration (Email, Phone) | Email + Phone / Total num of Registration | Registered_user, Email_Verified, Phone_Verified | Business Type | String | Commercial, Residential | Type of Business
TSV Adoption | sum(TSV Registered) whereTSV Registered='Yes' | TSV registred | Service/Product_subscription | varchar | Tv ,mobile,internet/Broadband | type of service selected by user
Email verified | count of tsv registered where tsv type='email' | tsv type,tsv registred | Registration Type | String | Web, App | Auto Registration
phone verified | count of tsv registered where tsv type='call' | tsv type,.tsv registred | Registration Date | DateTime | 2024-08-12T13:58:18+00:00 (Time Format) | User when register for the first time
Sms verified | count of tsv registered where tsv type='sms' | tsv type,tsv registred | Inception Date
Login Creation | user login timestamp |  | Verified Contact | String | Yes, No | Check whether the Contact has been verified or not
Email Success | (count(email_verified) where email_verified='Yes')/total registered user | email_verified,total registered user | Verification Type | Varchar | Email,Phone | Method used for verification
Phone Success | (count(phone_verified) where phone_verified='Yes')/total registered user | phone_verified,total registered user | Email_Verified | String | Yes, No | Whether the email has been verified or not
Account Success | Count of registered users where verification type is phoe or email / total customers | verification type, registered user, total customers | Phone_Verified | String | Yes, No | Whether the Phone number has been verified or not
|  |  | TSV Registered | String | Yes, No | User has registered for TSV
|  |  | TSV Factor Type | String | Email, SMS, Okta,Call | Type of TSV
|  |  | Engagement Channel | String | Digital, Call Center, Retail | At this point we are considering only digital
Last 7 days | (countD([GUID] where [LastLoginDate] >= DATEADD('day', 7, TODAY()))/ COUNTD([GUID]))*100 | GUID, Last Login Date
% of customer logging in last 3 months | (countD([GUID] where [LastLoginDate] >= DATEADD('month', -3, TODAY()))/ COUNTD([GUID]))*100 | GUID, Last Login Date | Email Contact | - | - | Need to confirm need to stored PII data or any attributes
|  |  | Email Exist | String | Yes, No
|  |  | Phone Exist | String | yes, No
|  |  | Phone Verified | String | yes, No
|  |  | User |  | Primary/ Secondary

## Customer_Profile_Updated (hidden)
Metric | Calculation | Columns | Data Type | Attribute | Description
Total Customers | Count of GUID | GUID (Account) | Varchar | Primary Key(Alphanumeric) | Identifier linking to customer
Customers Registered Successfully % | Reg_customers/ count(total_customers) | GUID (Account) | Varchar | Primary Key(Alphanumeric) | For login & password
|  | GUID 2 (User) | Varchar | User level (Foreign Key) | User level ID associated with primary account
Total GUID's | Count of Account GUID's | Total GUID (user)/total GUID(Account) | Int | Primary Key | Internal Key (6 - 8 digit)
Registered within 7 days | Customer registered in first 7 days | Registration Date | DateTime | 2024-08-12T13:58:18+00:00 (Time Format) | User when register for the first time
Success in Registring | count(Regisered_user) where registered_user='YES' | Registered User | String | Yes, No | Identifier linking to customer
Email Registration | (count(email_verified) where email_verified='Yes')/total registered user | Email_verified,Total registered user | String | Yes, No | Whether the email has been verified or not
Phone Registration | (count(phone_verified) where phone_verified='Yes')/total registered user | Phone_verified,Total registered user | String | Yes, No | Whether the Phone number has been verified or not
Both Registration (Email, Phone) | Email + Phone / Total num of Registration | Verification Type | Varchar | Email,Phone | Method used for verification
TSV Registered | sum(TSV Registered) whereTSV Registered='Yes' | TSV registered | String | Yes, No | User has registered for TSV
Email verified | count of tsv registered where tsv type='email' | Email Verified, TSV Type | String | Yes, No | Whether the email has been verified or not
phone verified | count of tsv registered where tsv type='call' | Phone Verified, TSV Type | String | Yes, No | Whether the phone has been verified or not
SMS verified | count of tsv registered where tsv type='sms' | Sms Verified, TSV Type | String | Yes, No | Whether the sms has been verified or not
Login Creation | user login timestamp | Registration Date | DateTime | 2024-08-12T13:58:18+00:00 (Time Format) | User login first time
Email Success | (count(email_verified) where email_verified='Yes')/total registered user | email_verified,total registered user | String | Yes, No | Whether the email has been verified or not
Phone Success | (count(phone_verified) where phone_verified='Yes')/total registered user | phone_verified,total registered user | String | Yes, No | Whether the phone has been verified or not
Account Success | Count of registered users where verification type is phone or email / total customers | verification type, registered user, total customers | String | Yes, No | Whether the account has been verified or not
Last 7 days | (countD([GUID] where [LastLoginDate] >= DATEADD('day', 7, TODAY()))/ COUNTD([GUID]))*100 | GUID, Last Login Date | Varchar
% of customer logging in last 3 months | (countD([GUID] where [LastLoginDate] >= DATEADD('month', -3, TODAY()))/ COUNTD([GUID]))*100 | GUID, Last Login Date | Varchar
UserType | Count of Primary, Secondary Users | Primary User ,Secondary User | String | Yes, No
User Authentication | Count of Authorized, Unauthorized | Authorized User, Unauth User | String | Yes, No
Notification Preference |  | Preference Type | String | Email/ Phone (Call/SMS)
Market |  |  | String | 29 cities we need to consider
Business Type | Count of commercial, Residential GUID | Business Type | String | Commercial, Residential
Service/ Product Subsc | Count of User under each category | Subscription Category | Varchar | Tv ,mobile,internet/Broadband
Registration Type |  | User GUID, Registration Type, Channel Type | String | Web,App, IVR,Retail
Account with Email | Count of registered users through Email | Email Exist | String | Yes, No
Account with Phone | Count of registered users through Phone | Phone Exist | String | Yes, No

## Data Model 2 for Activity (hidden)
Metrics | Calculation | Columns | Data Type | Attribute | Description | Column_source
Successful Authentication | Count of user GUID where Phone, Email or both verified | User GUID, Phone Verified , Email Verified | User GUID - Varchar, Phone Verified - Boolean or String, Email Verified - Boolean or String | Verified - 1 or 0 , Yes or No | AuthenticationSuccess
Authentication Sucess % | (Count of Authentication_Status as 'sucess'/ count of User GUID) *100 | User GUID, Authentication_Status | Authentication_Status - String, User GUID -VarChar | Authentication_Status - 'Successful', 'Failed' , 'Pending | Percentage of successful authentication
Number of Digital authentication | Count of User GUID where channel type is digital | User GUID, Channel Type | User GUID - Varchar, Channel Type - String | Channel Type - Digital or offline | Number of authentication done through digital channel
Number of offline authentication | Count of User GUID where channel type is offline | User GUID, Channel Type | User GUID - Varchar, Channel Type - String | Channel Type - Digital or offline | Number of authentication done through offline channel
Successful Authentication through Web | (Count of User GUID where registration type as web and channel type as digital / count of User GUID where channel as digital) *100 | User GUID, Registration Type, Channel Type | User GUID - Varchar, Registration Type - String | Registration Type - Web , App | Percentage of successful authentication through web
Successful Authentication through App | (Count of User GUID where registration type as App and channel type as digital / count of User GUID where channel as digital) *100 | User GUID, Registration Type, Channel Type | User GUID - Varchar, Registration Type - String, Channel Type - String | Registration Type - Web , App | Percentage of successful authentication through App
Successful Authentication through IVR | (Count of User GUID where registration type as IVR and channel type as offline / count of User GUID where channel as offline) *100 | User GUID, Registration Type, Channel Type | User GUID - Varchar, Registration Type - String, Channel Type - String | Registration Type - IVR, Retail | Percentage of successful authentication through IVR
Successful Authentication through Retail | (Count of User GUID where registration type as Retail and channel type as offline / count of User GUID where channel as offline) *100 | User GUID, Registration Type, Channel Type | User GUID - Varchar, Registration Type - String, Channel Type - String | Registration Type - IVR, Retail | Percentage of successful authentication through Retail
Recovery Sucess % | (Count of Recovery ID where Recovery_Status as 'sucess'/ count of Recovery ID) *100 | Recovery ID, Recovery Status | Recovery_Status - String, Recovery ID -VarChar | Recovery_Status - 'Requested', 'Inprogress', 'Completed' , 'Failed' | Percentage of successful recovery
Percentage of recovery using Phone | (Count of Recovery ID where Recovery_method as 'Phone' and Recovery status as success / count of Recovery ID) *100 | Recovery ID, RecoveryMethod | Recovery ID - Varchar, Recovery Method - String | Recovery Method - Phone, Email , Account | Percentage of successful recovery using phone
Percentage of recovery using Email | (Count of Recovery ID where Recovery_method as 'Email' and Recovery status as success / count of Recovery ID) *100 | Recovery ID, RecoveryMethod | Recovery ID - Varchar, Recovery Method - String | Recovery Method - Phone, Email , Account | Percentage of successful recovery using email
Percentage of recovery using Account | (Count of Recovery ID where Recovery_method as 'Account' and Recovery status as success / count of Recovery ID) *100 | Recovery ID, RecoveryMethod | Recovery ID - Varchar, Recovery Method - String | Recovery Method - Phone, Email , Account | Percentage of successful recovery using Account
TSV Authentication Sucess (in Percentage) | (Sum of TSV Registered where TSV Registered as 'Yes' / Sum of TSV Registered)*100 | TSV Registered | TSV Registered - String | TSV Registered - Yes, No | Percentage of successful TSV authentication
Percentage of TSV successful authentication via email | (Sum of TSV Registered where TSV Registered as 'Yes' and TSV Type as email / Sum of TSV Registered)*100 | TSV Registered , TSV Type | TSV Registered - String , TSV Type | TSV Registered - Yes, No TSV Type - Email, Call, SMS | Percentage of successful TSV authentication via email
Percentage of TSV successful authentication via Call | (Sum of TSV Registered where TSV Registered as 'Yes' and TSV Type as call / Sum of TSV Registered)*100 | TSV Registered , TSV Type | TSV Registered - String , TSV Type | TSV Registered - Yes, No TSV Type - Email, Call, SMS | Percentage of successful TSV authentication via call
Percentage of TSV successful authentication via SMS | (Sum of TSV Registered where TSV Registered as 'Yes' and TSV Type as SMS / Sum of TSV Registered)*100 | TSV Registered , TSV Type | TSV Registered - String , TSV Type | TSV Registered - Yes, No TSV Type - Email, Call, SMS | Percentage of successful TSV authentication via SMS
Authentication by Channel by method | Count of User GUID group by 'channel' and 'Auth method' | User GUID, Channel , Auth Method | Auth Method - String, Channel - String | Auth Method - Pwd, PIN, SQSA, SSN, TSV Channel - SMS, Email, Call | Authentication done through which channel and through which method
User logged in past 12 months | Count of User GUID where LastLoginDate is within past 12 months | User GUID, Last Login Date | User GUID - Varchar, Last Login Date - Date Time |  | Number of users logged in past 12 months
Login Recovery Success rate | (Count([Successful Recovery Attempts])/ Count([Recovery Attempts])) *100 | Recovery Status, Recovery Attempts |  | Recovery Status - Requested, InProgress, Completed , Failed
TSV Authentication Volume | Count of User GUID where TSV Registered = yes | TSV Registered | String | Yes, No
# calls related to authentication | Count of Authentication ID where channel type ='Call' | Count of Authentication ID where channel type as 'Call' | Authentication ID - Varchar Channel - String | Channel - SMS, Email, Call | Number of calls related to Authentication
Average Time from Order to Install | AVG(DATEDIFF 'day', [order date], [Install date]) | Order date, Install date (installation completion date) | DateTime |  | Average time taken from order to installation
Average Time from order to register | AVG(DATEDIFF 'day', [order date], [Registration date]) | Order date, registration date | DateTime |  | Average time taken from order to registration
Average Time from order to First Digital Contact | AVG(DATEDIFF 'day', [order date], [First Digital contact date]) | Order date, first digital contact date | DateTime |  | Average time from order to first digital contact
% of customers seeing an onboarding email | Count of User GUID where Onboarding email seen = True) / Count of user GUID)*100 | GUID, Onboarding email seen | Onboarding email seen - String, GUID - Varchar |  | Percentage of customers seeing an onboarding email
% of customer logging in last 3 months | (count of User GUID where LastLoginDate in past 3 months / COUNT of User GUID))*100 | GUID, Last Login Date | Varchar, DateTime |  | Percentage of customers logging in last 3 months
% of customers downloading the app | Count of User GUID where App Downloaded = True / Count of USer GUID *100 | GUID, App downloaded | Varchar, String |  | Percentage of customers downloading the app
TSV Reset Volume and Success Rate
% of Customers registering on F1
|  | Auth Method | String | Passwords, OTP | Method used for authentication
|  | OTP Expiration | DateTime |  | Timestamp indicating when the OTP expires
|  | OTP Sent Date | DateTime |  | Timestamp of when the OTP was sent to the user
|  | OTP verification Status | String | Verified, NotVerified, Expired | Status of the OTP verification process
Authentication ID, Customer ID, Auth Method, AuthAttemptDate - Same as above
|  | AuthAttemptDate | DateTime |  | Timestamp of the authenticaton attempt
|  | Channel Type | String | Web, App [Digital] | Indicates whether the authentication was performed via web or app
|  | AuthStatus | String | Successful, Failed, Pending | Result if the authentication attempt
|  | Channel Type | String | IVR, Retail [Offline] | Indicates whether the authentication was performed via IVR or retail
|  | AuthMethod | String / Integer | OTP, Push Notification
|  | AgentID | Varchar |  | Identifier for the retail agent handling the authentication
|  | Retail Location | String |  | Location or Store where the retail authentication took place
|  | Recovery ID | Varchar |  | Unique identifier for each recovery record
|  | Recovery Method | String | Phone, Email, Account Details | method used for recovery
|  | Recovery Status | String | Requested, InProgress, Completed , Failed | Status of the recovery request
|  | RecoveryRequestDate | DateTime |  | Timestamp of when the recovery request was made
|  | RecoveryCompletionDate | DateTime |  | Timestamp of when the recovery process was completed
|  | Recovery Failure Reason | String | Email failure,phone failure | Reason for failure, if the recovery was unsuccessful
|  | AuthSuccessID | Varchar |  | Unique Identifier for each authentication success record
|  | Channel Type | String | Email, Call, SMS | Indicates the channel used for authentication
|  | Auth Method | String | OTP, Password | Method used for authentication
|  | Auth Status | String | Successful, Failed | Result of the authentication attempt
|  | AuthenticationTimeLimit | String |  | Authentication timeout - OTP Expiry
|  | Resend OTP | String | Yes, No

## dashboard_metrics with formula (hidden)
Metric | Calculation | Columns Required | Source Table
Contact Information
Total Customers | Count of customers | GUID2 | edw.customer_dim | GUID
Regd Customers % | Reg_customers/ count(customers) | Reg_customers, Total Customers | edw.customer_guid_dtl_dim | Reg Customer
Total Customers
Total GUID | users / Profile | Guid , Guid2 |  | GUID
GUID 2
Accounts with Email | Count of GUID where email is present | GUID, Email Status (Has Email =True or False) | Contact table
Accounts with Verifed Email | Count of GUID where email verification status is verified | GUID, Email verification status | Contact table
Accounts with Phone | CountD of GUID where phone number is present | GUID, Phone Status (Has Phone number = True or False) | Contact table
Accounts with verified phone | CountD of GUID where phone verification status is verified | GUID, Phone verification status | Contact table
Age of Contact | Average age of accounts based on creation date | GUID, Account creation date |  |  | Check with Praveen ( age of contact - DoB)
Engagement
Average Time from Order to Install | AVG(DATEDIFF 'day', [order date], [Install date]) | Order date, Install date (installation completion date)
Average Time from order to register | AVG(DATEDIFF 'day', [order date], [Registration date]) | Order date, registration date
Average Time from order to First Digital Contact | AVG(DATEDIFF 'day', [order date], [First Digital contact date]) | Order date, first digital contact date | (Account Creation, First Login or First time user interacted with website)
% of customers seeing an onboarding email | CountD([GUID ID] where [Onboarding email seen] = True) / CountD([GUID]))*100 | GUID, Onboarding email seen
% of customer logging in last 3 months | (countD([GUID] where [LastLoginDate] >= DATEADD('month', -3, TODAY()))/ COUNTD([GUID]))*100 | GUID, Last Login Date |  | (last 30 days, 7 days)
% of customers downloading the app | (CountD([GUID] where [App Downloaded] = True) / CountD([GUID])*100 | GUID, App downloaded
Activity (Volume and Success Rate)
Authentication by channel by method (Pwd, SSN, SQSA,PIN) | Count([GUID ID]) group by 'channel' and'Auth method' | GUID, Channel, Auth Method
User logged in past 12 months | countD([GUID]) where LastLoginDate >= DATEADD('Month', -12, Today()) | GUID, Last Login Date
Authentication Success Rate | SUM(([Successful Authentication]) / Count([Auth Status])) *100 | Authentication Status, Auth Status
Login Recovery Success rate | (Count([Successful Recovery Attempts])/ Count([Recovery Attempts])) *100 | Recovery Status, Recovery Attempts
TSV Enrollment Success Rate | (sum(TSV Registered) whereTSV Registered='Yes' / sum(TSV Registered))*100 | TSV Registered
TSV Reset Volume | CountD(Recovery ID) where TSV Registered ='Yes' | Recovery Id, TSV Registered
TSV Authentication Volume | Count(TSV Registered) where TSV Registered = yes | TSV Registered
Split by Channel and Method | Group by Channel Type and Auth Method | Channel Type, Auth Method
# calls related to authentication | countD(Authentication ID) where channel type ='Call' | Authentication ID, Channel Type
Metrics from Registration and Authentication - Initiatives and Metrics

## Dashboard Metric (hidden)
Metric | Calculation | Columns Required | Source Table
% of Customers Registered | (Registered Customer/Total Customers)*100 | Registered Customers, Total Customers (Count of GUIDs)
First 7 | DateDiff('days', Registration date,7) | Registration date
Success in Registring | count(Regisered_user) where registered_user='YES' | Registered_user
Email Success | (count(email_verified) where email_verified='Yes')/total registered user | email_verified,total registered user
Phone Success | (count(phone_verified) where phone_verified='Yes')/total registered user | phone_verified,total registered user
Account Success | Count of registered users where verification type is phoe or email / total customers | verification type, registered user, total customers
Login Creation | user login timestamp
Atleast One Contact Verified | count of verification type | verification type
Email verified | Count of GUID where email verification status is verified | GUID, Email verification status
phone verified | CountD of GUID where phone number is present | GUID, Phone Status (Has Phone number = True or False)
Both verified(email,phone) | CountD of GUID where phone number & email="Yes" | GUID, Phone Status & email status=true
TSV Adoption | sum(TSV Registered) whereTSV Registered='Yes' | TSV registred
Authentication Success | count of digital & offline | channel type
Digital | count of channel type where channel type='Digital' | channel type
Offline | count of channel type where channel type='Offline' | channel type
Recovery Success | (Count([Successful Recovery Attempts])/ Count([Recovery Attempts])) *100 | Recovery Status, Recovery Attempts
Phone Success | CountD of GUID where phone verification status is verified | GUID, Phone verification status
TSV Auth Success | (sum(TSV Registered) whereTSV Registered='Yes' / sum(TSV Registered))*100 | TSV Registered
call success | count of tsv registered where tsv type='call' | tsv type,.tsv registred
sms success | count of tsv registered where tsv type='sms' | tsv type,tsv registred
Email Success | count of tsv registered where tsv type='email' | tsv type,tsv registred
Web Success | count of registation type where registartion type='web' | registration type
app success | count of registation type where registartion type='app' | registration type

## Data Model 2 Authentication (hidden)
Columns | Data Type | Attribute | Description
Authentication
Authentication ID | Varchar |  | Unique Identifier for each authentication record
Customer ID / GUID | Varchar |  | Identifier linking to customer
Auth Method | String | Passwords, OTP | Method used for authentication
Editable User Id | Boolean | True, False | Indicates if the user ID can be edited by the user
OTP Details
OTP Token | String / Integer |  | OTP value generated for authentication
OTP Expiration | DateTime |  | Timestamp indicating when the OTP expires
OTP Sent Date | DateTime |  | Timestamp of when the OTP was sent to the user
OTP verification Status | String | Verified, NotVerified, Expired | Status of the OTP verification process
Passwords
PasswordHash | Varchar |  | The hashed version of the user's password
PasswordLast Updated | DateTime |  | Timestamp of when the password was last updated
LastSuccessfulLoginDate | DateTime |  | Timestamp of last successful authentication
Authentication Success - Digital Channel
Authentication ID, Customer ID, Auth Method, AuthAttemptDate - Same as above
AuthAttemptDate | DateTime |  | Timestamp of the authenticaton attempt
Channel Type | String | Web, App | Indicates whether the authentication was performed via web or app
AuthStatus | String | Successful, Failed, Pending | Result if the authentication attempt
Authentication Success - offline Channel
Authentication ID, Customer ID, AuthAttemptDate - Same as above
Channel Type | String | IVR, Retail [Offline] | Indicates whether the authentication was performed via IVR or retail
AuthMethod | String / Integer | OTP
AgentID | Varchar |  | Identifier for the retail agent handling the authentication
Retail Location | String |  | Location or Store where the retail authentication took place
Recovery
Recovery ID | Varchar |  | Unique identifier for each recovery record
Recovery Method | String | Phone, Email, Account Details | method used for recovery
Recovery Status | String | Requested, InProgress, Completed , Failed | Status of the recovery request
RecoveryRequestDate | DateTime |  | Timestamp of when the recovery request was made
RecoveryCompletionDate | DateTime |  | Timestamp of when the recovery process was completed
Recovery Failure Reason | String |  | Reason for failure, if the recovery was unsuccessful
Method
Phone | Integer |  | phone number associated with the recovery request
Verification Status | String | Verified, Not Verified
Email Address | String |  | email address associated with the recovery request
Verification Status | String | Verified, Not Verified
Account Details
Security Questions | String |  | security questions used
Answer Status | String | Correct, Incorrect
TSV Auth Success
AuthSuccessID | Varchar |  | Unique Identifier for each authentication success record
Channel Type | String | Email, Call, SMS | Indicates the channel used for authentication
Auth Method | String | OTP, Password | Method used for authentication
Auth Status | String | Successful, Failed | Result of the authentication attempt
AuthenticationTimeLimit | DateTime |  | Authentication timeout - OTP Expiry