## Slide 1: CIAM Project Updates
18th October 2024

## Slide 2: CIAM Project Gantt. Status – 08th November 2024
Lagging as Per Plan
On Track as Per Plan
Activities |  | 12-Aug | 19-Aug | 26-Aug | 2-Sep | 9-Sep | 16-Sep | 23-Sep | 30-Sep | 7-Oct | 14-Oct | 21-Oct | 28-Oct | 4-Nov | 11-Nov | 18-Nov | 25-Nov | 2-Dec
Engineering | Individual Accesses & Azure AVD set up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Discovery & Requirement Gathering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Accesses and Environment Setup (AWS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Build Data Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Data Validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Data Transformation Flow (ETL) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Scheduling and Automation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Visualization | Business Goals & Data Sample |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Design Templates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stakeholder Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Deployment & Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3: CIAM Project Milestones – 08th November 2024
Milestone | Owner | Target Date | Progress This Week | Challenges/Dependencies
Profile Dashboard |  |  |  | 
Validate numbers for site = 186, correct metric calculation | BI/data | 8th Nov 2024 | Metrics validated/feedbacks worked | Few metrics are WIP for data/logic
Ingest all markets data for last 13 months in sandbox tables | Data | 11th Nov 2024 | Queries initiated and ingestion is WIP | Volumes of data and processing times
Switch tableau dashboard to new view and validate metrics | BI | 13th Nov 2024 | Yet to start | Availability of the complete data to switch
Create glue job to create aggregated view table | Data | 21th Nov 2024 | Glue jobs initiated and views are WIP | Volumes of data and processing times
Validate numbers for all sites, correct metric calculations | BI/data | 25th Nov 2024 | Yet to start | Ingestion of data into the tables
Ingest offline metrics to tables and dashboard | BI/data | TBD | Yet to start | Praveen to confirm source data/logic
Close on the pending metrics | BI/data | TBD | Yet to start | Praveen to confirm source data/logic
Activity Dashboard |  |  |  | 
Validate numbers for site = 186, correct metric calculation | BI/data | 8th Nov 2024 | Metrics validated/feedbacks worked | Few metrics are WIP for data/logic
Ingest all markets data for last 13 months in sandbox tables | Data | 11th Nov 2024 | Queries initiated and ingestion is WIP | Volumes of data and processing times
Switch tableau dashboard to new view and validate metrics | BI | 13th Nov 2024 | Yet to start | Availability of the complete data to switch
Align with business on pending derived metrics source/logic | BI/Data | 14th Nov 2024 | Yet to start | Availability of the complete data to switch
Create glue job to create aggregated view table | Data | 21th Nov 2024 | Glue jobs initiated and views are WIP | Volumes of data and processing times
Validate numbers for all sites, correct metric calculations | BI/data | 25th Nov 2024 | Yet to start | Ingestion of data into the tables
Close on the pending metrics | BI/data | TBD | Yet to start | Praveen to confirm source data/logic
Lagging as Per Plan
On Track as Per Plan
All Markets Ingestion
Nov 11
Ingest all the markets data
Business Brainstorming
Nov 14
Review with Matt & team
Final Stakeholder Review
Nov 27
Final stakeholder review before production
Production Go Live
Dec 4
Automate Glue ETL
Nov 21
Validate identified metrics
Gather feedback for scope
Automate ingestion and view creation
Publish dashboard to tableau
Nov 4
Nov 11
Nov 18
Nov 25
Dec 2
Nov 11

## Slide 4: CIAM Project Status – 08th November 2024
Table | Pending Tasks | Owner | Target Data | Challenges/Dependencies
Account Dim | Here we can fill individual metric/column level gaps |  |  | 
 |  | Dipesh |  | 
 |  | Data |  | 
 |  | Shital |  | 
 |  | Praveen |  | Praveen to confirm source data
Profile Dim | Ingestion of data of 13 months is in progress and timing out in Athena | Shital/Gokul |  | 3X (Account Dim) records are to be ingested into AWS, Athen is timing out
 | Team is working to ingest data in batches/partitions and other alternatives | Shital/Gokul |  | Increase Athena time out as an exception
Adobe Daily Fact | Data was ingested without the time key | Shital/Gokul |  | 
Auth Daily Fact | Data was ingested without the time key | Shital/Gokul |  | 
Auth User Fact | Data was ingested without the time key | Shital/Gokul |  | 
Lagging as Per Plan
On Track as Per Plan

## Slide 5: CIAM Dashboard Status 08th November 2024
Weekly Key Headlines
Upcoming Week Key Activities
Risks & Issues
Project Phase | EXECUTION
Schedule Health | Lagging | 
Budget Health | On Track | 
Scope Health | Defined | 
Key Activities | Status | Owner | Target Date
Validation of data metrics for the complete data set available now and creation of calculated field views |  | Data Team | 8th November 2024
Mapping & Data Validation of KPIs/Metrics on Tableau Dashboard, Finishing the Dashboards Design |  | BI Team | 16th November 2024
Data team has received the access for the complete data and in the process of data and aggregated metrics validation (Target 08th November 2024)
  Original the target date for data validation was 30th October 2024 but currently team is facing delays due to
    Aggregation queries failing in Athena due to high volumes of data
    Mobile app data tables are missing and Cox team is helping us get access to the same
BI Team is continuing with enhancing the Tableau dashboards basis the actual data tables
(Target 08th November 2024)
  Challenge is that the calculated fields and custom queries slowing down the dashboard refresh time
    Team is working with the option to create calculated fields view at source level only to reduce refresh time
    Refining visuals iteratively basis the business feedback and new data availability
Data validation with the Praveen for all the identified metrics/additional KPIs to be included as part of the model (Ongoing)
Program Objective
CIAM Dashboard: Provide support on building an integrated data staging layer & Tableau dashboards with integration to AWS S3 with Snowflake & Adobe as the source of the data to drive and integrated data layer for better BI & Insights, Auto extraction of information and design ETL procedures to create Customer and Customer activity level views in Tableau
Lagging as Per Plan
On Track as Per Plan
R/I | SEVERITY | DESCRIPTION | PLANNED DATE | MITIGATION/UPDATES
R | H | ETL Glue Jobs Configuration, Testing & Deployment environment for enabling the continuous data ingestion and integration | 09/23/2024 | Team is testing out the AWS glue crawlers and job scheduling basis the current access to identify/mitigate any challenges early
R | M | Data quality and validation of the complete data set, any data issues may delay the timelines as the access was delayed and in progress | 09/23/2024 | Team is iteratively validating the new data and data refresh to ensure the data integrity and values are in line with business understanding
R | M | Ongoing data validation and alignment to the business logic/metrics leading to iterative development/changes of the BI dashboard | 10/07/2024 | Collaborating with Praveen/Cox Teams to get the business inputs and vision for continuous improvements

## Slide 6: CIAM Dashboard Status 08th November 2024
Weekly Key Headlines
Upcoming Week Key Activities
Risks & Issues
Project Phase | EXECUTION
Schedule Health | Lagging | 
Budget Health | On Track | 
Scope Health | Defined | 
Key Activities | Status | Owner | Target Date
Populating and validation of the sub metrics into the sub metric column and calculated columns for 7 days/30 days |  | Data Team | 8th November 2024
Explore the OMNI Db table and add a new metric and validate |  | Data Team | 8th November 2024
Mapping & Values Validation of KPIs/Metrics on Tableau Dashboard, Finishing the Dashboards Design |  | BI Team | 16th November 2024
Data Team has created the ETL Glue jobs to automate the data transformation basis the requirement for Tableau dashboard to reduce the load on visualization layer and make it more robust to changes (Target 08th November 2024)
Data team has created below data model for Health Scorecard Dashboard with 4 Tables (Target 08th November 2024)
  HC_Mapping_Master – Complete – Mapping IDs for each metric and OS Type
  HC_Source_Data_Actual – Complete – Actual data from source tables with the raw values
  HC_Source_Data_Calc – WIP – Calculated metrics & sub metrics data (Sub Metrics calculation are WIP)
  HC_DB_Metrics_Cal – WIP – Calculated metrics for 7 days/30 days metrics (Calculation Validation is WIP)
BI Team is updating the Tableau Dashboard visuals are being updated to the new table views with calculated fields with validation of all the metrics on Tableau (Target 16th November 2024)
  Trend charts and yesterday column in Tableau are done and going through data validation
Program Objective
Health score dashboard: Provide support on building an integrated data staging layer & Tableau dashboards with integration to AWS S3 as Adobe is the source of the data. Auto extraction of information and design ETL procedures. CB Dashboard: Provide support to create a query for new metrics for dashboard. (Profile and Adoption). And create a table in Athena for visualization through Tableau
Lagging as Per Plan
On Track as Per Plan
R/I | SEVERITY | DESCRIPTION | PLANNED DATE | MITIGATION/UPDATES
I | M | Health score: HC_DB_Metrics_Cal table, getting few columns as NaN. Team is working on reviewing the transformation code in Glue |  | Team is reviewing the code in Python on Glue to fix the issues
R | H | CB: while fetching the data for 2 years and 2 months source query was exhausted. Tried to create partitioned table but unable to complete the same |  | Planning to create a separate tables for 2 years for profile and adoption section

## Slide 7: Thank You