## Slide 1: CIAM Project Updates
13th Dec 2024

## Slide 2: CIAM Project - Milestones and Planned Action items
Lagging as Per Plan
On Track as Per Plan
Stakeholder Review
Dec 5
Ingest all the markets data
Production Go Live ( Soft Launch)
Dec 6
Publish dashboard to tableau
Business Review
Dec 20
Validate identified metrics
Add Digital adoption
Add Email/SMS Bounce
ETL Automation & Dashboard Optimization
Dec 26
Dec 2
Dec 6
Dec 23
Dec 30
Activity | Owner | Target Date | Status | Challenges/Dependencies
Data Engineering |  |  |  | 
Glue Job review, Optimization opportunity, other ETL alternative identification and proposal and Alignment with Cox Infra Team for deployment on Prod and Non/Prod environment | Data | 24th Dec 2024 | In Progress | Alignment with Cox Infra team for Cost and Performance optimization review and approval
Enhancement to existing data model to include additional business metrics For Ex. Emails, SMS bounce rates etc | Data | 20th Dec 2024 | In Progress | Availability of Data sources and Business Logic
Query and Aggregate View optimization ( For existing and additional data sources) | Data | 23rd Dec 2024 | On Going | 
Bi Development |  |  |  | 
Ingestion and Validation of new metrics based on enhanced data model | BI/ data | 20th Dec 2024 | TBD | Availability of Data sources and Business Logic
Review for continuous improvement from design, performance and optimization opportunities | BI Data | 31st Dec 2024 | On Going | 

## Slide 3: CIAM Project - Metric Gaps
View | Metric | Owner | Target Data
Profile | Contact Data | Metrics are sourced from BAU tables, need to switch too Vibe Hub | Post Vibe Hub Launch
 | TSV Enrolled & Factor | Current Splunk source is understated, need to update source query in Splunk and fix | Jan’25
 | Authorized Status | Source not identified for billing permission at profile level | Jan’25 TBD Discussing with IDM BIS team
 | Email/SMS Bounce | Source recently identified | 20 Dec
 | Digital Adoption Buckets | In process | 20 Dec
Activity | Auto -Registration | Source is unknown, in discussion with OSS/DSS | Jan’25/Feb’25
 | Auto –Registration Pwd Chg | Source is unknown, in discussion with OSS/DSS | Jan’25
 | Offline Authentication | Source is being identified, once identified need to ingest into AWS | TBD
 | Online Authentication Failure | Waiting on DSS to move to AWS | TBD
 | Login Methods (link/otp) | Source is unknown, will need to implement tracking | TBD
Lagging as Per Plan
On Track as Per Plan

## Slide 4: CB & Health Scorecard - Milestones and Planned Action items
Lagging as Per Plan
On Track as Per Plan
Designing a Dynamic Data Model
20th Dec
-Ingest all the markets data
-Validate identified metrics
Production Go Live ( Soft Launch)
Dec 27th
-Create Data Ingestion Pipeline
- Test the data ingestion from source
Queries and Aggregate Optimization
Jan 03rd
Add Digital adoption
Add Email/SMS Bounce
Stakeholder Review and Deployment
TBD
Dec 20th
Dec 27th
Jan 03rd
TBD
Activity | Owner | Target Date | Status | Challenges/Dependencies
Data Engineering |  |  |  | 
Designing a dynamic data model for the hierarchical metrics for Health Scorecard | Data | 20th Dec 2024 | In Progress | Availability of Data sources and Business Logic
Ingesting the source CB & Health Scorecard data into the AWS tables | Data | 27th Dec 2024 | In Progress | Alignment with Cox Infra team for Cost and Performance optimization review and approval
Query and Aggregate View optimization ( For existing and additional data sources) | Data | 3rd Jan 2024 | Yet to Start | 
BI Development |  |  |  | 
Tableau dashboard framework for CB & Health Scorecard | BI/ data | 29th Nov 2024 | Completed | Creating a Data Staging layer for multiple calculated fields in the excel dashboards
Ingest all features data into the Tableau Dashboards | BI Data | 31st Dec 2024 | In Progress | Availability of Data sources and Business Logic

## Slide 5: UAT Testing Project - Milestones and Planned Action items
Validate all 11 Dashboards for data validations till September
Nov 13th 2024
-Identify the data gaps with dashboards
-Validate the working of the visuals
Work with the data teams for open data issues and refreshing the data
Nov 27th 2024
-Raise the data issues with the data team
-Validate the dashboards post the data updates
Work with the data teams for open data issues and refreshing the data
Dec 15th 2024
-Validated all dashboards with updated data
-Continuously refresh all 22 data sources
Post Migration Support
TBD
Nov 13th
Nov 27th
Dec 15th
Dec 30th
Activities | Owner | Target Date | Status | Challenges/Dependencies
Tableau UAT Testing |  |  |  | 
Publish all the 11 identified dashboards to dev server and refresh the data sources till the most current dates available in data tables | BI Team | 13th Nov 2024 | Completed | Access to the Tableau dev servers, share point and the UAT tracker
Complete the parity testing of all the dashboards, views, worksheets for the metrics between the dev and the prod server | BI Team | 27th Nov 2024 | Completed | Access to the Tableau dev & prod servers to do parity analysis
Collaborate with the data teams for open issues and keep sharing the deltas and issues identified with data parity | BI Team | 2nd Dec 2024 | Completed | Manually refresh the data as the dev server extract scheduling is not working
Iterate the parity testing and identification of metrics with gaps and complete the validation & UAT testing process | BI Team | 15th Dec 2024 | In Progress | Completion of ongoing data updates and successful refresh of the data in tableau dev server
Support team with the production deployment and provide support on any issues identified | BI Team | Yet to Start | Yet to Start | TBD
Medium Risk
Low Risk

## Slide 6: Thank You

## Slide 7: CIAM Project Milestones – 13th December 2024
Milestone | Owner | Target Date | Progress This Week | Challenges/Dependencies
Profile Dashboard |  |  |  | 
Validate numbers for site = 186, correct metric calculation | BI/data | 8th Nov 2024 | Metrics validated/feedbacks worked | Few metrics are WIP for data/logic
Ingest all markets data for last 13 months in sandbox tables | Data | 11th Nov 2024 | Completed | AWS Infra challenges and aggregated view development delayed
Switch tableau dashboard to new view and validate metrics | BI | 13th Nov 2024 | Completed | Dashboard switched to aggregated view. Metrics re-formation and data validation WIP. ETA 21st Nov
Create glue job to incremental data load | Data | 25th Nov 2024 | Completed | Volumes of data and processing times
Validate numbers for all sites, correct metric calculations | BI/data | 5th Dec 2024 | Complete | Ingestion of data into the tables
Ingest offline metrics to tables and dashboard | BI/data | TBD | Yet to start | Praveen to confirm source data/logic
Close on the pending metrics | BI/data | TBD | Yet to start | Praveen to confirm source data/logic
Activity Dashboard |  |  |  | 
Validate numbers for site = 186, correct metric calculation | BI/data | 8th Nov 2024 | Completed | Few metrics are WIP for data/logic
Ingest all markets data for last 13 months in sandbox tables | Data | 11th Nov 2024 | Completed | Volumes of data and processing times
Switch tableau dashboard to new view and validate metrics | BI | 13th Nov 2024 | Completed | Availability of the complete data to switch
Align with business on pending derived metrics source/logic | BI/Data | 14th Nov 2024 | Completed | Need some inputs from business as well
Validate numbers for all sites, correct metric calculations | BI/data | 5th Dec 2024 | Completed | Ingestion of data into the tables
Close on the pending metrics | BI/data | TBD | Yet to start | Praveen to confirm source data/logic
Lagging as Per Plan
On Track as Per Plan
All Markets Ingestion
Nov 11
Ingest all the markets data
Business Brainstorming
Nov 14
Review with Matt & team
Final Stakeholder Review
Nov 27
Final stakeholder review before production
Production Go Live
Dec 6
Automate Glue ETL
Nov 21
Validate identified metrics
Gather feedback for scope
Automate ingestion and view creation
Publish dashboard to tableau
Nov 4
Nov 11
Nov 18
Nov 25
Dec 2
Dec 6

## Slide 8: CIAM Project Status – 22nd November 2024
Table | Pending Tasks | Owner | Target Data | Challenges/Dependencies
Account Dim |  |  |  | 
Profile Dim | Ingestion of data of 13 months is in progress and timing out in Athena | Shital/Gokul |  | 3X (Account Dim) records are to be ingested into AWS, Athen is timing out
 | Team is working to ingest data in batches/partitions and other alternatives | Shital/Gokul |  | Increase Athena time out as an exception
Adobe Daily Fact | Data was ingested without the time key | Shital/Gokul |  | 
Auth Daily Fact | Data was ingested without the time key | Shital/Gokul |  | 
Auth User Fact | Data was ingested without the time key | Shital/Gokul |  | 
Lagging as Per Plan
On Track as Per Plan

## Slide 9: CIAM Project Gantt. Status – 22nd November 2024
Lagging as Per Plan
On Track as Per Plan
Activities |  | 12-Aug | 19-Aug | 26-Aug | 2-Sep | 9-Sep | 16-Sep | 23-Sep | 30-Sep | 7-Oct | 14-Oct | 21-Oct | 28-Oct | 4-Nov | 11-Nov | 18-Nov | 25-Nov | 6-Dec
Engineering | Individual Accesses & Azure AVD set up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Discovery & Requirement Gathering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Accesses and Environment Setup (AWS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Build Data Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Data Validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Data Transformation Flow (ETL) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Scheduling and Automation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Visualization | Business Goals & Data Sample |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Design Templates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stakeholder Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Deployment & Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 10: CIAM Dashboard Status 22nd November 2024
Weekly Key Headlines
Upcoming Week Key Activities
Risks & Issues
Project Phase | EXECUTION
Schedule Health | Lagging | 
Budget Health | On Track | 
Scope Health | Defined | 
Key Activities | Status | Owner | Target Date
Validation of data metrics for the complete data set available now and creation of calculated field views |  | Data Team | 19th November 2024
Mapping & Data Validation of KPIs/Metrics on Tableau Dashboard, Finishing the Dashboards Design |  | BI Team | 27th November 2024
All Market Data loaded into AWS layer
Aggregated views with feedback implemented for Account and Profile Fact tables
BI Team changed Tableau dashboard data source from Athena tables to aggregated views
Business review of CIAM dashboards planned with Matt and Elliot on 22nd Nov
Data validation with the Praveen for all the identified metrics/additional KPIs to be included as part of the model (Ongoing)
Program Objective
CIAM Dashboard: Provide support on building an integrated data staging layer & Tableau dashboards with integration to AWS S3 with Snowflake & Adobe as the source of the data to drive and integrated data layer for better BI & Insights, Auto extraction of information and design ETL procedures to create Customer and Customer activity level views in Tableau
Lagging as Per Plan
On Track as Per Plan
R/I | SEVERITY | DESCRIPTION | PLANNED DATE | MITIGATION/UPDATES
R | H | ETL Glue Jobs Configuration, Testing & Deployment environment for enabling the continuous data ingestion and integration | 09/23/2024 | Team is testing out the AWS glue crawlers and job scheduling basis the current access to identify/mitigate any challenges early
R | M | Data quality and validation of the complete data set, any data issues may delay the timelines as the access was delayed and in progress | 11/11/2024 | Team is iteratively validating the new data and data refresh to ensure the data integrity and values are in line with business understanding
R | M | Ongoing data validation and alignment to the business logic/metrics leading to iterative development/changes of the BI dashboard | 11/14/2024 | Collaborating with Praveen/Cox Teams to get the business inputs and vision for continuous improvements

## Slide 11: Health Scorecard/CB Dashboard Status 22nd November 2024
Weekly Key Headlines
Upcoming Week Key Activities
Risks & Issues
Project Phase | EXECUTION
Schedule Health | Lagging | 
Budget Health | On Track | 
Scope Health | Defined | 
Key Activities | Status | Owner | Target Date
Populating and validation of the sub metrics for the remaining features for Health Scorecard |  | Data Team | 30th November 2024
Mapping & Values Validation of KPIs/Metrics on Tableau Dashboard, Finishing the Dashboards Design for all features |  | BI Team | 30th November 2024
Health score dashboard:
BI Team has completed the Health Scorecard dashboards integrated directly to AWS S3 for the Smart Help Feature
Additionally BI team is working on including new metrics including the containment rates for Smart help Features
Data team is working on the data layer for the ingestion of all the remaining self help features and derived metrics
Data & BI teams are working together with Praveen for the validation of metrics for both CB & Health scorecard
CB Dashboard:
Data Team has completed the Athena queries to fetch the data for BI dashboards visualization
BI team is working on 1st cut dashboard to be taken to business stakeholders for review on metrics
Program Objective
Health score dashboard: Provide support on building an integrated data staging layer & Tableau dashboards with integration to AWS S3 as Adobe is the source of the data. Auto extraction of information and design ETL procedures. CB Dashboard: Provide support to create a query for new metrics for dashboard. (Profile and Adoption). And create a table in Athena for visualization through Tableau
Lagging as Per Plan
On Track as Per Plan
R/I | SEVERITY | DESCRIPTION | PLANNED DATE | MITIGATION/UPDATES
I | M | Health score: Multiple features have variations with the derived metrics calculation, so team has to perform addnl. due diligence |  | Team is reviewing the code in Python on Glue to fix the issues
R | H | CB: Data for CB dashboard is yet to be ingested into AWS S3 so the team will have to create ingestion and integration pipelines post data availability |  | Team is leveraging Athena queries and Glue jobs so the development curve is less later