## Project Plan
Activities |  | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04
Data Engg | Individual Accesses & Azure AVD set up
Discovery & Requirement Gathering
Accesses and Enviroment Setup (AWS)
Data Ingestion (S3)
Creating Pipeline & Orchestration
Data Transformation (Sage maker/ ETL)
Query (Athena)
Monitoring & Automation
Testing & Validation
BI Development | Sample data procurement & understanding
Visualization Design
Development
Connections with Athena/AWS
Testing & Validation
Deployment & Support

## Data Architecture
Implementation Roadmap for AWS
Data Sources | Data Classification
Oracle DB (Table-Schema) | Structured
Glu/ Sage maker/ PySpark/ EMR
Splunk (Log files) | Unstructured |  | AWS DMS, Custom Scripts, Lambda function,Direct Upload
|  |  |  | AWS S3 (Landing Stage) | Sage Maker (ETL) - Staging Stage |  | S3 Processed Data Bucket | Athena
S3 (File) | Semi Structured
CRM Application (DB) | Structured
|  |  |  | S3 as Primary data lake to store raw data | Data Cleansing, Filter, Transformation |  |  | Athena to run SQL queries on the data stored in S3 processed bucket
[6 empty] | Tableau |  | Athena External Table

## Data Model 1-customer data (hidden)
|  | remove | [6 empty] | Remove | Remove
Column Name | GUID | user_id | Registration_Type | Registation_Time | Verified Contact | Verified_type | Market(US cities) | Business_Type | Email_Info | Contact_details | Recovery type | TSV registered | TSV Adoption type | Feature | Engagement Channel | Login_timestamp | Service/Product_subscription | Address | Registration_type | Customer_status | Customer vistied to site
Data Type | UNIQUEIDENTIFIER | VarChar(50) | String | Timestamp | string(5 char) | VarChar(50) | string (50 char) | string (50 char) | VarChar(50) | Int(10) | varchar(50) | string | string | string | string
Attributes | Primary Key(Alphanumeric) |  | Auto-Registration | user when register first time | Yes/No | Email/Phone | 29 cities we need to consider | Commercial/Residential |  |  | Phone/SMS/email | Yes/No | Email/call/SMS/Okta | Authentication/Password Reset/User ID Recovery | Digital, Call Center, Retail
Sample Data | 001 6311 064810301 | praveenp | web/App | 2024-08-12T13:58:18+00:00 | Yes/No | Email |  | Residential | Praveen.Prabhakaran@cox.com | XXXX | Email | Yes/No | Okta | Password Reset | Digital

## Data Model 1 customer data
Column | Data Type | Attribute | Description
GUID (Account) | Varchar | Primary Key(Alphanumeric) | Identifier linking to customer
GUID 2 (User)
Registration Type | String | Web, App | Auto Registration
Registration Time | DateTime | 2024-08-12T13:58:18+00:00 (Time Format) | User when register for the first time
Verified Contact | String | Yes, No | Check whether the Contact has been verified or not
Verification Type | Varchar | Email,Phone | Method used for verification
Market | String | 29 cities we need to consider | 26 Cities (Need to check)
Business Type | String | Commercial, Residential | Type of Business
Service/Product_subscription | varchar | Tv ,mobile,internet/Broadband | type of service selected by user
Email_Verified | String | Yes, No | Whether the email has been verified or not
Phone_Verified | String | Yes, No | Whether the Phone number has been verified or not
Recovery Type | String | Varchar | Phone, SMS, Email
TSV Registered | String | Yes, No | User has registered for TSV
TSV Adoption Type | String | Email, SMS, Okta,Call | Type of TSV
Feature | String | Authentication, Password Recovery, User ID Recovery | Which feature is adopted by user
Engagement Channel | String | Digital, Call Center, Retail | At this point we are considering only digital

## Data Model 2 for Authentication
Columns | Data Type | Attribute | Description
Authentication
Authentication ID | Varchar |  | Unique Identifier for each authentication record
Customer ID / GUID | Varchar |  | Identifier linking to customer
Auth Method | String | Passwords, OTP | Method used for authentication
OTP Details
OTP Expiration | DateTime |  | Timestamp indicating when the OTP expires
OTP Sent Date | DateTime |  | Timestamp of when the OTP was sent to the user
OTP verification Status | String | Verified, NotVerified, Expired | Status of the OTP verification process
Authentication Success - Digital Channel
Authentication ID, Customer ID, Auth Method, AuthAttemptDate - Same as above
AuthAttemptDate | DateTime |  | Timestamp of the authenticaton attempt
Channel Type | String | Web, App [Digital] | Indicates whether the authentication was performed via web or app
AuthStatus | String | Successful, Failed, Pending | Result if the authentication attempt
Authentication Success - offline Channel
Authentication ID, Customer ID, AuthAttemptDate - Same as above
Channel Type | String | IVR, Retail [Offline] | Indicates whether the authentication was performed via IVR or retail
AuthMethod | String / Integer | OTP, Push Notification
AgentID | Varchar |  | Identifier for the retail agent handling the authentication
Retail Location | String |  | Location or Store where the retail authentication took place
Recovery
Recovery ID | Varchar |  | Unique identifier for each recovery record
Recovery Method | String | Phone, Email, Account Details | method used for recovery
Recovery Status | String | Requested, InProgress, Completed , Failed | Status of the recovery request
RecoveryRequestDate | DateTime |  | Timestamp of when the recovery request was made
RecoveryCompletionDate | DateTime |  | Timestamp of when the recovery process was completed
Recovery Failure Reason | String | Email failure,phone failure | Reason for failure, if the recovery was unsuccessful
TSV Auth Success
AuthSuccessID | Varchar |  | Unique Identifier for each authentication success record
Channel Type | String | Email, Call, SMS | Indicates the channel used for authentication
Auth Method | String | OTP, Password | Method used for authentication
Auth Status | String | Successful, Failed | Result of the authentication attempt
AuthenticationTimeLimit | String |  | Authentication timeout - OTP Expiry
Resend OTP | String | Yes, No

## Data Model 2 Authentication (hidden)
Columns | Data Type | Attribute | Description
Authentication
Authentication ID | Varchar |  | Unique Identifier for each authentication record
Customer ID / GUID | Varchar |  | Identifier linking to customer
Auth Method | String | Passwords, OTP | Method used for authentication
Editable User Id | Boolean | True, False | Indicates if the user ID can be edited by the user
OTP Details
OTP Token | String / Integer |  | OTP value generated for authentication
OTP Expiration | DateTime |  | Timestamp indicating when the OTP expires
OTP Sent Date | DateTime |  | Timestamp of when the OTP was sent to the user
OTP verification Status | String | Verified, NotVerified, Expired | Status of the OTP verification process
Passwords
PasswordHash | Varchar |  | The hashed version of the user's password
PasswordLast Updated | DateTime |  | Timestamp of when the password was last updated
LastSuccessfulLoginDate | DateTime |  | Timestamp of last successful authentication
Authentication Success - Digital Channel
Authentication ID, Customer ID, Auth Method, AuthAttemptDate - Same as above
AuthAttemptDate | DateTime |  | Timestamp of the authenticaton attempt
Channel Type | String | Web, App | Indicates whether the authentication was performed via web or app
AuthStatus | String | Successful, Failed, Pending | Result if the authentication attempt
Authentication Success - offline Channel
Authentication ID, Customer ID, AuthAttemptDate - Same as above
Channel Type | String | IVR, Retail [Offline] | Indicates whether the authentication was performed via IVR or retail
AuthMethod | String / Integer | OTP
AgentID | Varchar |  | Identifier for the retail agent handling the authentication
Retail Location | String |  | Location or Store where the retail authentication took place
Recovery
Recovery ID | Varchar |  | Unique identifier for each recovery record
Recovery Method | String | Phone, Email, Account Details | method used for recovery
Recovery Status | String | Requested, InProgress, Completed , Failed | Status of the recovery request
RecoveryRequestDate | DateTime |  | Timestamp of when the recovery request was made
RecoveryCompletionDate | DateTime |  | Timestamp of when the recovery process was completed
Recovery Failure Reason | String |  | Reason for failure, if the recovery was unsuccessful
Method
Phone | Integer |  | phone number associated with the recovery request
Verification Status | String | Verified, Not Verified
Email Address | String |  | email address associated with the recovery request
Verification Status | String | Verified, Not Verified
Account Details
Security Questions | String |  | security questions used
Answer Status | String | Correct, Incorrect
TSV Auth Success
AuthSuccessID | Varchar |  | Unique Identifier for each authentication success record
Channel Type | String | Email, Call, SMS | Indicates the channel used for authentication
Auth Method | String | OTP, Password | Method used for authentication
Auth Status | String | Successful, Failed | Result of the authentication attempt
AuthenticationTimeLimit | DateTime |  | Authentication timeout - OTP Expiry