## Sheet1
Rsisk |  | Completed | [8 empty] | Week 1 AWS Access for Glue job Dev | [6 empty] | Week 2 Glue job Development in Progress | [6 empty] | Week 3 Glue Job Dev Completed | [6 empty] | Week 4 ETL Testing Completed | [6 empty] | Week 5 Full Data integration in Tableau | [6 empty] | Week 6 Documentation and training
Dependencies |  | WIP
Delayed
Phase | Sr. No | Acitivty | Category | RAID | Status | time axis 2024-11-04 to 2024-12-15
Requirement/Access | 1 | Required access to all database in AICOE Account (Mobile_data schema needs to be updated) | Data Engg | COX | bar: 2024-11-04 to 2024-11-10
Development | 2 | Setup AWS Glue Environment in AICOE Account | Data Engg | COX | bar: 2024-11-04 to 2024-11-10
Development | 3 | Create a Glue Data Catalog to manage metadata. | Data Engg
Development | 4 | Set up IAM roles for Glue and S3 access(Need to check if we can use existing IAM Role or Need to create new) | Data Engg | COX
Development | 5 | Create Glue Crawlers | Data Engg
Development | 6 | Configure Glue Crawlers to scan source Athena tables and populate the Data Catalog. | Data Engg
Development | 7 | Develop ETL Jobs | Data Engg
Development | 8 | Create Glue ETL jobs to: | Data Engg
Development | 9 | Extract data from source Athena tables. | Data Engg
Development | 10 | Transform data according to mapping specifications (cleaning, aggregating using existing query). | Data Engg
Development | 11 | Load transformed data into target Athena tables.(Need to check where we can create target tables in which schema) | Data Engg
Development | 12 | Schedule jobs for regular execution (e.g., daily, hourly). | Data Engg
Testing | 13 | Unit test Glue jobs to ensure they function as expected. | Data Engg | bar: 2024-11-25 to 2024-11-29
Testing | 14 | Validate data integrity and accuracy after loading. | Data Engg | bar: 2024-11-25 to 2024-11-29
Deployment | 15 | Deploy Glue Jobs | Data Engg | Cox | bar: 2024-12-02 to 2024-12-06
Deployment | 16 | Deploy the developed Glue jobs to the production environment. | Data Engg | bar: 2024-12-02 to 2024-12-06
Deployment | 17 | Set up Monitoring | Data Engg | bar: 2024-12-02 to 2024-12-06
Deployment | 18 | Configure AWS CloudWatch to monitor job executions and alert on failures. | Data Engg | Cox | bar: 2024-12-02 to 2024-12-06
Deployment | 19 | Data Validation | Data Engg | bar: 2024-12-02 to 2024-12-06
Deployment | 20 | Perform data validation checks to ensure data consistency between source and target tables. | Data Engg
Reporting | 21 | Connect Tableau to Athena | BI Reporting |  | Completed | bar: 2024-12-02 to 2024-12-06
Reporting | 22 | Set up Tableau to connect to Athena using the provided JDBC/ODBC drivers. | BI Reporting |  | Completed | bar: 2024-12-02 to 2024-12-06
Reporting | 23 | Develop Dashboards | BI Reporting | bar: 2024-12-02 to 2024-12-06
Reporting | 24 | Create live dashboards in Tableau using the newly created fact tables. | BI Reporting | bar: 2024-12-02 to 2024-12-06
Documentation and Training | 25 | Create Documentation | Overall
Documentation and Training | 26 | Document the ETL process, including job configurations and data transformation logic. | Overall
Support | 27 | Monitor Performance | Overall
Support | 28 | Regularly monitor the performance of ETL jobs and Tableau dashboards. | Overall